## Test Scenario
Scenario ID | Module | Test Scenario | Priority
TS-001 | Registration | Verify user can register with valid details | High
TS-002 | Registration | Verify registration with existing username | High
TS-003 | Login | Verify login with valid credentials | High
TS-004 | Login | Verify login with invalid credentials | High
TS-005 | Login | Verify login with empty fields | High
TS-006 | Products | Verify products are displayed correctly | Medium
TS-007 | Products | Verify product categories work correctly | Medium
TS-008 | Product Details | Verify product details are displayed correctly | Medium
TS-009 | Cart | Verify user can add a product to cart | High
TS-010 | Cart | Verify user can remove a product from cart | High
TS-011 | Cart | Verify cart displays selected products correctly | High
TS-012 | Cart | Verify cart total is calculated correctly | High
TS-013 | Order | Verify user can place an order with valid details | High
TS-014 | Order | Verify order form validation | High
TS-015 | Navigation | Verify navigation links work correctly | Medium
TS-016 | Contact | Verify user can submit a message through the Contact form. | Medium
TS-017 | Logout | Verify user can log out successfully | Medium
TS-018 | UI components | Verify UI components display consistently and clearly | High

## Test Cases
Test Case ID | Scenario ID | Test Case | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status
TC-001 | TS-001 | Verify registration with valid details | User is on DemoBlaze home page | Unique valid username and password | 1. Click Sign up 2. Enter username 3. Enter password 4. Click Sign up | User should be sign up successfully | User signup successfully | Pass
TC-002 | TS-002 | Verify registration with existing username | User is on DemoBlaze home page | Existing username and password | 1. Click Sign up 2. Enter existing username 3. Enter password 4. Click Sign up | Display a message that indicate user already exist. | Pop up "This user already exist messege" | Pass
TC-003 | TS-003 | Verify login with valid credentials | User is on DemoBlaze home page | Valid username and password | 1. Click login 2. Enter username 3. Enter password 4. Click login | User should be successfully logged in. | User login successfully | Pass
TC-004 | TS-004 | Verify login with invalid username | User is on DemoBlaze home page | Invalid user name A valid password | 1. Click login 2. Enter invalid username 3. Enter password 4. Click login | An appropriate error message should be displayed indicating that the username or password is invalid. | Pop up "User does not exist message" | Pass
TC-005 | TS-004 | Verify login with invalid password | User is on DemoBlaze home page | An existing valid username Wrong password | 1. Click login 2. Enter username 3. Enter invalid password 4. Click login | An appropriate error message should be displayed indicating that the username or password is invalid. | Pop up "Wrong password" message | Pass
TC-006 | TS-005 | Verify login with empty fields | User is on DemoBlaze home page | Empty username and password | 1. Click login 2. Leave username and password fields empty 3. Click login | An appropriate error message should be displayed indicating that the requireed fields must be filled. | Pop up message "Please fill out Username and Password" | Pass
TC-007 | TS-006 | Verify products' images , name , price , discription display correctly | User logged in and on the Products page | N/A | 1. Navigate to the Products section 2. View the displayed products 3. Check product images , names , prices and descriptions | Display products images , name , price and description correctly | Display products images , name , price and description correctly | Pass
TC-008 | TS-007 | Verify each category displays correctly. | User logged in and on the Products page | Product categories | 1. Navigate to the Products section. 2.Click each available product category. 3. Observe the displayed products. | Display products related to each category correctly. | Display products related to each category correctly. | Pass
TC-009 | TS-008 | Verify product details are displayed correctly. | User logged in and on the Products page | Any available product | 1. Select a product 2. View the product details page | The selected product's details should be displayed correctly. | The selected product's details displayed correctly. | Pass
TC-010 | TS-009 | Verify user can add a product to cart | User logged to the system | Any available product | 1. Select a product 2. Click add to cart 3. Navigate to the cart page | The selected product should be added to the cart and displayed correctly. | Pop up "Product added" message and selected product display in the cart | Pass
TC-011 | TS-009 | Verify user can add more than one product to cart | User logged to the system and on the products page | Two products | 1. Select the first product 2. Click add to cart 3. Select another product 4. Click add to cart 5. Navigate to the cart page | Both selected products should be added to the cart and displayed correctly | Both selected products added to the cart and displayed correctly | Pass
TC-012 | TS-010 | Verify user can remove a product from cart | User logged in and has at least one product in the cart | Selected product | 1. Navigate to the Cart page. 2. Click the delete button for the selected product | The selected product should be removed from the cart. | The selected product removed from the cart. | Pass
TC-013 | TS-011 | Verify cart displays selected products correctly | User logged to the system and has at least one product in the cart. | Selected products | 1. Navigate to the Cart page. 2. View the products displayed in the cart | Cart displays selected products' details correctly. | Cart displays selected products' details correctly. | Pass
TC-014 | TS-012 | Verify cart total is displayed correctly | User logged to the system and has at least one product in the cart. | Selected products | 1. Navigate to the Cart page. 2. Note the prices of all products in the cart. 3. Calculate the expected total. 4. Compare the calculated total with the displayed total | The displayed cart total should equal the sum of the prices of all products in the cart. | Total displays correctly | Pass
TC-015 | TS-013 | Verify place an order with valid details | User logged to the system and has at least one product in the cart. | Valid personal details and valid credit card details | 1. Navigate to the Cart page. 2. Click Place Order. 3. Enter valid personal details 4. Enter valid credit card details. 5. Click purchase | The order should be placed successfully and a payment/order confirmation message should be displayed. | The order placed successfully and a payment/order confirmation message displayed. | Pass
TC-016 | TS-014 | Verify order form validation with invalid details | User logged to the system and has at least one product in the cart. | Invalid or incomplete personal and/or credit card details | 1. Navigate to the Cart page. 2. Click Place Order. 3. Enter invalid or incomplete details. 4. Click Purchase. | The system should prevent the order from being placed and display an appropriate validation or error message. | The order placed successfully and a payment/order confirmation message displayed. | Fail
TC-017 | TS-014 | Verify order form validation with empty required fields | User logged to the system and has at least one product in the cart. | Empty required fields | 1. Navigate to the Cart page. 2. Click Place Order. 3. Leave the required fields empty. 4. Click Purchase. | The system should prevent the order from being placed and display an appropriate validation or error message. | Pop up message "Please fill out Name and Creditcard." | Pass
TC-018 | TS-015 | Verify Home link navigate to the Home page correctly. | User is on DemoBlaze home page |  | Click the Home link | The Home page should be displayed correctly. | The Home page displayed correctly. | Pass
TC-019 | TS-015 | Verify Contact link opens the Contact form correctly | User is on DemoBlaze home page |  | Click Contact link | The Contact form/message box should be displayed correctly. | The Contact form/message box displayed correctly. | Pass
TC-020 | TS-015 | Verify About us link navigate to the About us section correctly. | User is on DemoBlaze home page |  | Click About us link | The About Us section should be displayed correctly. | The About Us section displayed correctly. | Pass
TC-021 | TS-015 | Verify cart link navigate to the Cart correctly. | User is on DemoBlaze home page |  | Click cart link | The Cart page should be displayed correctly, showing the selected products or an empty cart as applicabl | The Cart page displayed correctly, showing the selected products or an empty cart as applicabl | Pass
TC-022 | TS-015 | Verify login link navigate to the login page correctly. | User is on DemoBlaze home page |  | Click login link | The Log In form should be displayed correctly. | The Log In form displayed correctly. | Pass
TC-023 | TS-015 | Verify Sign up link navigate to the Sign up page correctly. | User is on DemoBlaze home page |  | Click Sign up link | The Sign Up form should be displayed correctly. | The Sign Up form displayed correctly. | Pass
TC-024 | TS-016 | Verify user can submit a message through the Contact form. | User is on the DemoBlaze Home page. | Valid name, email, and message | 1. Click the Contact link 2. Enter a valid name 3. Enter valid email address 4. Enter a message 5. Click send message | The system should successfully submit the message and display an appropriate confirmation message. | Pop up "Thanks for the message!!" | Pass
TC-025 | TS-016 | Verify user cannot submit the Contact form without required details | User is on the DemoBlaze Home page. | Empty required fields | 1. Click the contact link 2. Leave the required fields empty 3. Click send Message | The system should prevent submission and display an appropriate validation message. | Pop up "Thanks for the message!!" | Fail
TC-026 | TS-017 | Verify user can log out successfully | User is logged in to the system |  | 1. Click the Log Out link | The user should be successfully logged out of the system. | The user successfully logged out of the system. | Pass
TC-027 | TS-018 | Verify UI components display consistently and clearly | User is on the DemoBlaze website. |  | 1. View all pages. 2. Check the navigation bar, buttons, links, product cards, images, text, and other UI components. | UI components should be displayed consistently, clearly, and without visual issue | Some UI components are not properly aligned. The “Products” heading is partially cut off on the left side, and some Cart page elements have inconsistent alignment and spacing. | Fail

## Defect Log
Bug ID | Module | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Screenshots
BUG-001 | Order | System allows order placement with invalid/incomplete details | 1. Open the Cart 2.Click Place Order 3.Enter invalid/incomplete details 4.Click Purchase | Order should not be placed and an error/validation message should be displayed | Order was placed successfully and confirmation was displayed | High | High
BUG-002 | Contact | System allows to submit contact form without required fields | 1. Click contact 2.Leave required fields empty 3.Click send message | Form should prevent submission and display validation message | “Thanks for the message!!” was displayed even though fields were empty | Medium | High
BUG-003 | UI Components | Cart page UI components are misaligned and spacing is inconsistent | 1. Open Cart 2. Observe Products section 3. Observe Total section and page layout | Cart page components should be properly aligned with consistent spacing and layout. | Cart page components are misaligned, with inconsistent spacing between the navigation bar, product list, and Place Order section. | Medium | Medium